## Requirements
ID | Area | Requirement | Decision / Clarification | Codex Implementation | Acceptance Criteria / Test | Source / Traceability | Owner | Priority | Status | Verification | Codex Notes
SR-001 | Passage progression | World 1 passage difficulty remains consistent | All World 1 passages same standard; length increases after every 150 passages | Keep complexity profile constant across batches; configure length ladder separately | Passage specifications use consistent difficulty; length milestones follow approved map | Conversation: passage equivalence | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-001-consistent-difficulty.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/passage-progression.ts. Length ladder (80..260 words) and complexity profile are configuration placeholders; replace with the approved map values.
SR-002 | Revisit | Return previously struggled passages | Previously unsuccessful passage can be revisited for confidence, without blocking next passage | Persist passage-specific struggle/revisit eligibility; schedule a revisit while continuing new daily passage | Learner can revisit prior passage; next passage still available; no readiness evidence falsely substituted | Conversation: revisit decision | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-002-revisit.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/revisit.ts.
SR-003 | Equivalence | Next daily passage is ordinary practice equivalence | New daily passage of same difficulty is acceptable practice; repeat old passage supports confidence | Do not force extra replacement passages merely for practice; preserve special formal confirmation-form rules | Normal progression never blocked for an equivalent passage; formal readiness uses canonical equivalence rules | Conversation: equivalence; AC-37–41 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-003-equivalence.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/equivalence.ts.
SR-004 | Support | Provide model comprehension as support | Only comprehension support is access to best possible comprehension | Show approved BPC after attempt as support; tag subsequent attempts as assisted | BPC available; exposure logged; assisted evidence not treated as first independent attempt | Conversation: support; AC-19 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-004-bpc-support.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/model-answer-support.ts.
SR-005 | Freshness | Stale evidence after inactivity | Two weeks of inactivity makes evidence stale | Track last learner activity; mark evidence stale after 14 complete days inactivity; verify precise boundary with Codex | At 14-day boundary state follows approved timing convention; no silent certification from stale evidence | Conversation: 2-week decision; AC-44–45 | Codex | High | Implemented (TDD); provisional parameter awaiting confirmation | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-005-inactivity-stale.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/inactivity.ts. Boundary convention is switchable (default: stale at exactly 14 complete days). Still needs Codex/product confirmation.
SR-006 | Threshold | Pilot comprehension pass threshold | Consider 60 as provisional starting threshold; calibrate after 3–4 weeks of go-live using population scores | Parameterize threshold and lifecycle; do not hard-code; collect score distributions by passage/learner | Pilot threshold clearly provisional; calibrated change versioned and tested; final value not assumed approved | Conversation: 60 discussion; AC-54–56 | Codex | High | Implemented (TDD); provisional parameter awaiting confirmation | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-006-pilot-threshold.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pilot-threshold.ts. 60 shipped as provisional pilot v1, approved=false. Final value not assumed.
SR-007 | Calibration | Population-based calibration | Review average scores across passages and students after 3–4 weeks; choose appropriate standard | Create aggregate analytics with cohort size, score distribution, passage/RS splits and effective-date versioning | Calibration report available; threshold changes explicitly approved, not automatically deployed | Conversation: post-launch calibration; AC-55–56 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-007-calibration-report.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/calibration-report.ts. Report logic only; no data source wired yet.
SR-008 | ASR | Editable speech-to-text transcript | Show browser STT transcript and let learner correct text | Display transcript in editable text area; retain raw transcript and corrected submission separately | Learner sees and edits transcript before submitting; correction recorded; no ASR-only failure | Conversation: ASR; AC-21 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-008-editable-transcript.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/editable-transcript.ts. Pure logic. Not yet wired into the UI component.
SR-009 | Browser APIs | Use default browser speech APIs | Browser-native speech-to-text and text-to-speech | Use supported browser SpeechRecognition/webkitSpeechRecognition and speechSynthesis with capability detection | Works on supported browsers; unsupported API receives graceful fallback; no paid speech dependency | Conversation: browser APIs | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-009-browser-speech-apis.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/browser-speech.ts. Capability detection + fallback plan; TTS detection lives in lib/narrator.ts to respect FR-037.
SR-010 | Progression | No learner blocking | Continue with next passage regardless of oral/comprehension outcome | Separate progression from readiness state; always enable next assigned passage | Failed oral or comprehension attempt does not block next passage; history remains intact | Conversation: nonblocking progression; AC-36 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-010-no-blocking.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/non-blocking.ts.
SR-011 | Oral feedback | News-reader model and mimicry | When oral reading is weak, replay news-reader rendition and invite learner to mimic | Offer browser TTS replay and optional oral retry; record support status | Learner can replay and mimic; not forced to stop progress; oral evidence remains separate | Conversation: oral feedback | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-011-mimicry.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/mimicry.ts. Pure logic. Not yet wired into the UI.
SR-012 | Architecture | Knowledge Map remains authority | No additional per-passage readiness lifecycle author role | Implement readiness from frozen knowledge map in runtime, not by generating new content artifacts | No Role 8 lifecycle author; runtime behavior traceable to canonical map | Conversation: role simplification; AC-32–36 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-012-knowledge-map-authority.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/roles.ts.
SR-013 | Pipeline | Eight production creators and independent QA gates | Each of Roles 1–8 has its own stage-specific independent QA | Require creator self-check then separate QA PASS before next stage | No downstream stage consumes unapproved WIP; 8 stage gates enforced | Conversation: pipeline design | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-013-stage-gates.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/gates.ts. Immutable gate state machine; not yet driving a live content job.
SR-014 | Pipeline role | Role 1: Passage Specification | Role 1 produces only its owned artifact | Create role-specific prompt; input must be approved upstream; output stored WIP; no QA self-certification | Role 1 output complete, bounded, provenance recorded and independently reviewable | Conversation: Roles 1 creator | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-014-role1-creator.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-015 | Pipeline QA | Role 1 QA: Passage Specification | Independent stage-specific QA; no repairs by QA | Validate role-specific requirements; issue PASS or FAIL with defect routing | QA PASS only on zero blockers; FAIL reports exact owner and evidence | Conversation: Roles 1 QA | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-015-role1-qa.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-016 | Pipeline role | Role 2: Passage Authoring | Role 2 produces only its owned artifact | Create role-specific prompt; input must be approved upstream; output stored WIP; no QA self-certification | Role 2 output complete, bounded, provenance recorded and independently reviewable | Conversation: Roles 2 creator | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-016-role2-creator.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-017 | Pipeline QA | Role 2 QA: Passage Authoring | Independent stage-specific QA; no repairs by QA | Validate role-specific requirements; issue PASS or FAIL with defect routing | QA PASS only on zero blockers; FAIL reports exact owner and evidence | Conversation: Roles 2 QA | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-017-role2-qa.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-018 | Pipeline role | Role 3: Assessment Authoring | Role 3 produces only its owned artifact | Create role-specific prompt; input must be approved upstream; output stored WIP; no QA self-certification | Role 3 output complete, bounded, provenance recorded and independently reviewable | Conversation: Roles 3 creator | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-018-role3-creator.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-019 | Pipeline QA | Role 3 QA: Assessment Authoring | Independent stage-specific QA; no repairs by QA | Validate role-specific requirements; issue PASS or FAIL with defect routing | QA PASS only on zero blockers; FAIL reports exact owner and evidence | Conversation: Roles 3 QA | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-019-role3-qa.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-020 | Pipeline role | Role 4: Meaning Units | Role 4 produces only its owned artifact | Create role-specific prompt; input must be approved upstream; output stored WIP; no QA self-certification | Role 4 output complete, bounded, provenance recorded and independently reviewable | Conversation: Roles 4 creator | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-020-role4-creator.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-021 | Pipeline QA | Role 4 QA: Meaning Units | Independent stage-specific QA; no repairs by QA | Validate role-specific requirements; issue PASS or FAIL with defect routing | QA PASS only on zero blockers; FAIL reports exact owner and evidence | Conversation: Roles 4 QA | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-021-role4-qa.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-022 | Pipeline role | Role 5: Best Possible Comprehension | Role 5 produces only its owned artifact | Create role-specific prompt; input must be approved upstream; output stored WIP; no QA self-certification | Role 5 output complete, bounded, provenance recorded and independently reviewable | Conversation: Roles 5 creator | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-022-role5-creator.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-023 | Pipeline QA | Role 5 QA: Best Possible Comprehension | Independent stage-specific QA; no repairs by QA | Validate role-specific requirements; issue PASS or FAIL with defect routing | QA PASS only on zero blockers; FAIL reports exact owner and evidence | Conversation: Roles 5 QA | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-023-role5-qa.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-024 | Pipeline role | Role 6: Scoring Contract | Role 6 produces only its owned artifact | Create role-specific prompt; input must be approved upstream; output stored WIP; no QA self-certification | Role 6 output complete, bounded, provenance recorded and independently reviewable | Conversation: Roles 6 creator | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-024-role6-creator.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-025 | Pipeline QA | Role 6 QA: Scoring Contract | Independent stage-specific QA; no repairs by QA | Validate role-specific requirements; issue PASS or FAIL with defect routing | QA PASS only on zero blockers; FAIL reports exact owner and evidence | Conversation: Roles 6 QA | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-025-role6-qa.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-026 | Pipeline role | Role 7: Attempt Outcome Contract | Role 7 produces only its owned artifact | Create role-specific prompt; input must be approved upstream; output stored WIP; no QA self-certification | Role 7 output complete, bounded, provenance recorded and independently reviewable | Conversation: Roles 7 creator | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-026-role7-creator.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-027 | Pipeline QA | Role 7 QA: Attempt Outcome Contract | Independent stage-specific QA; no repairs by QA | Validate role-specific requirements; issue PASS or FAIL with defect routing | QA PASS only on zero blockers; FAIL reports exact owner and evidence | Conversation: Roles 7 QA | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-027-role7-qa.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-028 | Pipeline role | Role 8: Final JSON Assembly | Role 8 produces only its owned artifact | Create role-specific prompt; input must be approved upstream; output stored WIP; no QA self-certification | Role 8 output complete, bounded, provenance recorded and independently reviewable | Conversation: Roles 8 creator | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-028-role8-creator.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-029 | Pipeline QA | Role 8 QA: Final JSON Assembly | Independent stage-specific QA; no repairs by QA | Validate role-specific requirements; issue PASS or FAIL with defect routing | QA PASS only on zero blockers; FAIL reports exact owner and evidence | Conversation: Roles 8 QA | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-029-role8-qa.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/creator.ts + qa.ts + role-specs.ts. Role-specific prompt, creator output check and independent QA (no repair, direct owner routing).
SR-030 | Routing | Direct owner routing | Each QA sends defects directly to originating owner, not simply preceding gate | Common defect record: defect_id, violated_rule, evidence, owner_role, return_to_role, affected_dependencies | Injected into all 16 role/QA prompts; tested cross-stage defects route correctly | Conversation: harmonization decision | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-030-defect-routing.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/defects.ts + qa.ts. Cross-stage routing demonstrated via Role 6 -> Role 3 (primary item); other rules default to the stage under QA.
SR-031 | Routing | Dependency-aware invalidation | Regenerate/revalidate only affected downstream artifacts | Maintain dependency DAG and artifact version hashes; invalidate impacted nodes after corrections | Unrelated QA PASS artifacts retained; affected descendants revalidated | Conversation: harmonization decision | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-031-dependency-invalidation.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/dag.ts.
SR-032 | Routing | Escalation for authority conflict | Contradictory Knowledge Map/schema cannot be resolved by agents | Escalate with exact conflicting citations; no local invented precedence | Conflict blocks release and produces explicit escalation | Conversation: routing contract; AC-01–03 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-032-authority-conflict.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/escalation.ts.
SR-033 | Final validator | Final QA consumes every approved gate output | Inputs include Role 8 assembly, approved Roles 1–7 outputs, QA results, schema and frozen knowledge map | Verify input manifest and QA status per source artifact | Missing upstream QA PASS blocks final acceptance | Conversation: final validator | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-033-final-input-manifest.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/final-validator.ts.
SR-034 | Final validator | Strict JSON parser | Mandatory independent machine or fidelity check | Run real parser on serialized bytes | Malformed JSON rejected | Conversation: Role 8 QA; AC-57–59 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-034-strict-json.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/strict-json.ts.
SR-035 | Final validator | Duplicate keys | Mandatory independent machine or fidelity check | Use parser hook rejecting duplicate object keys | Duplicate key fixture fails | Conversation: Role 8 QA; AC-57–59 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-035-duplicate-keys.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/strict-json.ts.
SR-036 | Final validator | JSON Schema | Mandatory independent machine or fidelity check | Validate canonical schema with real validator | Wrong type/required field/enum fails | Conversation: Role 8 QA; AC-57–59 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-036-json-schema.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/package-schema.ts (ajv 8.17.1). Added devDependency ajv 8.17.1.
SR-037 | Final validator | Referential integrity | Mandatory independent machine or fidelity check | Resolve every ID against approved artifact registry | Dangling and cross-passage refs fail | Conversation: Role 8 QA; AC-57–59 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-037-referential-integrity.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/referential-integrity.ts.
SR-038 | Final validator | Upstream fidelity | Mandatory independent machine or fidelity check | Diff approved passage, assessment, MU, BPC, scoring and attempt contracts | Any unauthorized alteration fails | Conversation: Role 8 QA; AC-57–59 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-038-upstream-fidelity.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/fidelity.ts.
SR-039 | Final validator | Version and hashes | Mandatory independent machine or fidelity check | Recompute required canonical hashes and verify package lock | Stale hash/version fails | Conversation: Role 8 QA; AC-57–59 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-039-version-hashes.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/version-lock.ts.
SR-040 | Final validator | Executable test evidence | Mandatory independent machine or fidelity check | Capture command, validator version, result and failure details | NOT_EXECUTED cannot PASS | Conversation: Role 8 QA; AC-57–59 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-040-executable-evidence.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/evidence.ts.
SR-041 | Final validator | Final QA is terminal production gate | FINAL_JSON_QA_PASS only if all mandatory checks executed and pass | Emit one final QA result per package; route defects to owner | PASS permits approved package promotion; FAIL never promotes | Conversation: Role 8 QA | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-041-terminal-gate.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/terminal-gate.ts.
SR-042 | Storage | WIP and approved separation | All generated artifacts under pipeline/wip; independently approved exact artifacts under pipeline/approved | Use configured Windows paths; only QA moves/copies approved exact artifact; downstream reads approved | No stage reads WIP as authoritative; hashes match approved copy | Project pipeline decisions | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-042-wip-approved-separation.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/storage.ts. Windows-path policy over an in-memory backend; real file-system backend not added.
SR-043 | Comprehension | Free spoken explanation prompt | Learner explains passage freely rather than being forced to answer pointed questions | Present fixed open prompt; capture free speech and editable transcript; use canonical semantic fact map | Learner free-response scored semantically; no exact wording requirement | Project comprehension discussion; AC-15,20 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-043-free-explanation.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/free-explanation.ts.
SR-044 | Comprehension | Semantic recall and uncertainty | Paraphrase allowed; omission, contradiction, unsupported and unresolved distinct | Use approved fact IDs and semantic evidence states; prevent ASR uncertainty from automatic failure | Equivalent paraphrase credited; unsupported inference not P1 recall; uncertainty preserved | Project P1 clarification; AC-20–21 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-044-semantic-recall.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/semantic-recall.ts.
SR-045 | Scoring | First-attempt independence | Assisted performance not silently converted into independent readiness | Persist attempt_role, assistance flag, evidence type and immutable outcomes | Original independent evidence unchanged after model-answer exposure | AC-19, AC-33, AC-43 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-045-first-attempt-independence.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/model-answer-support.ts.
SR-046 | Scoring | P10 primary and aggregation | Apply approved 4-item P10 blueprint and primary-item rule | Read designated primary item from approved assessment; apply canonical aggregation | 3/4 with primary correct passes; 3/4 with primary wrong fails where canonical rule applies | AC-16–17; role 7 prompt | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-046-p10-primary.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/p10-scoring.ts. Aggregation (3 of 4 + primary required) inferred from the acceptance examples; confirm against canonical map.
SR-047 | Oral | Separate oral and comprehension gates | No compensation across oral/comprehension | Persist separate results and readiness flags; orchestrate per frozen rules | Oral pass cannot override comprehension fail or vice versa | AC-36, AC-42 | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-047-separate-gates.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/separate-gates.ts.
SR-048 | Quality | Good-enough-to-ship | Reject real blockers; do not demand theoretical perfection | QA categories BLOCKER vs NON_BLOCKING; PASS and stop on zero blockers | Minor stylistic issues do not cause rework | Conversation: ship quickly | Codex | High | Implemented (TDD) | Unit tests pass 2026-10-08: hosted-app/tests/unit/sr/sr-048-good-enough-to-ship.test.ts; full suite 976/976; tsc clean | Code: hosted-app/lib/sr/pipeline/qa.ts (needsRework).

## Knowledge Map AC Index
Acceptance ID | Acceptance Criterion | Source
AC-01 | One authoritative canonical source | Attached Final Knowledge Map Acceptance Criteria
AC-02 | No hidden normative dependencies | Attached Final Knowledge Map Acceptance Criteria
AC-03 | Version precedence is unambiguous | Attached Final Knowledge Map Acceptance Criteria
AC-04 | Matrix integrity | Attached Final Knowledge Map Acceptance Criteria
AC-05 | Correct learner delivery order | Attached Final Knowledge Map Acceptance Criteria
AC-06 | Strand distribution invariant | Attached Final Knowledge Map Acceptance Criteria
AC-07 | RS/topic independence | Attached Final Knowledge Map Acceptance Criteria
AC-08 | Every RS is a genuine independent reading competency | Attached Final Knowledge Map Acceptance Criteria
AC-09 | No comprehension-dependent RS definition | Attached Final Knowledge Map Acceptance Criteria
AC-10 | P1→P10 progression is executable | Attached Final Knowledge Map Acceptance Criteria
AC-11 | Construction counts and evidence minimums must agree | Attached Final Knowledge Map Acceptance Criteria
AC-12 | RS05 contradiction resolved | Attached Final Knowledge Map Acceptance Criteria
AC-13 | RS12 contradiction resolved | Attached Final Knowledge Map Acceptance Criteria
AC-14 | Subsection evidence minima are numeric | Attached Final Knowledge Map Acceptance Criteria
AC-15 | P1→P10 comprehension progression remains fixed | Attached Final Knowledge Map Acceptance Criteria
AC-16 | P10 mixed-mastery coverage is explicit | Attached Final Knowledge Map Acceptance Criteria
AC-17 | Primary P10 item is explicitly identified | Attached Final Knowledge Map Acceptance Criteria
AC-18 | One defensible answer per scored item | Attached Final Knowledge Map Acceptance Criteria
AC-19 | Instructional mastery and independent readiness remain separate | Attached Final Knowledge Map Acceptance Criteria
AC-20 | One deterministic scoring specification | Attached Final Knowledge Map Acceptance Criteria
AC-21 | ASR uncertainty never becomes automatic learner error | Attached Final Knowledge Map Acceptance Criteria
AC-22 | Accent fairness is explicit | Attached Final Knowledge Map Acceptance Criteria
AC-23 | COUNT-100 is deterministic | Attached Final Knowledge Map Acceptance Criteria
AC-24 | Third/quartile segmentation is deterministic | Attached Final Knowledge Map Acceptance Criteria
AC-25 | Universal sample validity precedes RS scoring | Attached Final Knowledge Map Acceptance Criteria
AC-26 | General quality floor is considered explicitly | Attached Final Knowledge Map Acceptance Criteria
AC-27 | Opportunity-count fairness | Attached Final Knowledge Map Acceptance Criteria
AC-28 | Fifteen RS-specific baselines | Attached Final Knowledge Map Acceptance Criteria
AC-29 | No cross-RS raw metric comparison | Attached Final Knowledge Map Acceptance Criteria
AC-30 | Complete-round composites only | Attached Final Knowledge Map Acceptance Criteria
AC-31 | Baseline mastery does not require artificial improvement | Attached Final Knowledge Map Acceptance Criteria
AC-32 | One authoritative readiness ontology | Attached Final Knowledge Map Acceptance Criteria
AC-33 | `CONFIRMED_READY` closure semantics are explicit | Attached Final Knowledge Map Acceptance Criteria
AC-34 | Baseline-mastery status is not confused with certification | Attached Final Knowledge Map Acceptance Criteria
AC-35 | All 15 competencies are required | Attached Final Knowledge Map Acceptance Criteria
AC-36 | Oral and comprehension gates remain independent | Attached Final Knowledge Map Acceptance Criteria
AC-37 | Form-equivalence rules are fully present | Attached Final Knowledge Map Acceptance Criteria
AC-38 | One authoritative form-equivalence version | Attached Final Knowledge Map Acceptance Criteria
AC-39 | Confirmation form supply is operationally defined | Attached Final Knowledge Map Acceptance Criteria
AC-40 | Every generated readiness form passes the full content gate | Attached Final Knowledge Map Acceptance Criteria
AC-41 | Readiness-form identity is separate from registry passage identity | Attached Final Knowledge Map Acceptance Criteria
AC-42 | Oral/comprehension orchestration is deterministic | Attached Final Knowledge Map Acceptance Criteria
AC-43 | Retry lottery is prohibited | Attached Final Knowledge Map Acceptance Criteria
AC-44 | Confirmed evidence has an explicit freshness model | Attached Final Knowledge Map Acceptance Criteria
AC-45 | Recency numbers may remain provisional | Attached Final Knowledge Map Acceptance Criteria
AC-46 | Every one of the 150 rows is generation-complete | Attached Final Knowledge Map Acceptance Criteria
AC-47 | Row-level safety tags are explicit | Attached Final Knowledge Map Acceptance Criteria
AC-48 | PG1–PG12 are all mandatory | Attached Final Knowledge Map Acceptance Criteria
AC-49 | Exact 100 words never overrides quality | Attached Final Knowledge Map Acceptance Criteria
AC-50 | Nearby-duplicate QA uses learner order | Attached Final Knowledge Map Acceptance Criteria
AC-51 | First 100 sessions preserve confidence | Attached Final Knowledge Map Acceptance Criteria
AC-52 | Band-A readiness represents all 15 competencies | Attached Final Knowledge Map Acceptance Criteria
AC-53 | Functional Band-B transition must be validated empirically | Attached Final Knowledge Map Acceptance Criteria
AC-54 | Numeric thresholds have declared status | Attached Final Knowledge Map Acceptance Criteria
AC-55 | Comprehension hard gates also require calibration | Attached Final Knowledge Map Acceptance Criteria
AC-56 | Whole-gate calibration is required | Attached Final Knowledge Map Acceptance Criteria
AC-57 | Every structural invariant has an automated test | Attached Final Knowledge Map Acceptance Criteria
AC-58 | Boundary/edge-case test suite exists | Attached Final Knowledge Map Acceptance Criteria
AC-59 | No unresolved contradiction remains | Attached Final Knowledge Map Acceptance Criteria

## Role and QA Matrix
Role | Creator | Independent QA | Input Rule | Advancement Gate | Routing Contract | Harmonization
1 | Passage Specifier | Role 1 QA | Approved prior stage | Independent QA PASS required | Direct owner routing + impacted downstream regeneration | Harmonization pending
2 | Passage Author | Role 2 QA | Approved prior stage | Independent QA PASS required | Direct owner routing + impacted downstream regeneration | Harmonization pending
3 | Assessment Author | Role 3 QA | Approved prior stage | Independent QA PASS required | Direct owner routing + impacted downstream regeneration | Harmonization pending
4 | Meaning-Unit Author | Role 4 QA | Approved prior stage | Independent QA PASS required | Direct owner routing + impacted downstream regeneration | Harmonization pending
5 | Best Possible Comprehension Author | Role 5 QA | Approved prior stage | Independent QA PASS required | Direct owner routing + impacted downstream regeneration | Harmonization pending
6 | Scoring Contract Author | Role 6 QA | Approved prior stage | Independent QA PASS required | Direct owner routing + impacted downstream regeneration | Harmonization pending
7 | Attempt-Outcome Author | Role 7 QA | Approved prior stage | Independent QA PASS required | Direct owner routing + impacted downstream regeneration | Harmonization pending
8 | Final JSON Assembler | Role 8 QA | Approved prior stage | Independent QA PASS required | Direct owner routing + impacted downstream regeneration | Harmonization pending

## Read Me
SpeedReader Codex Requirements Tracker | 2026-10-08
Scope | Decisions and clarifications in discussion, eight role/QA chain, final validation, selected frozen AC cross-references
Important | Decision recorded does not mean code implemented or tested.
Provisional decisions | 60 threshold and exact inactivity-boundary mechanics require confirmation/verification.
Knowledge Map index | AC-01 through AC-59 are indexed; detailed source text remains authoritative.
Harmonization | Global routing contract has been designed but not yet applied to every prompt.
Code review | Existing repository implementation has not been verified in this workbook.
Next action | All 48 requirements implemented with TDD (unit level). Open: confirm SR-005 boundary, SR-006 threshold, SR-046 aggregation; wire runtime modules into the UI; add content-side prompts run.